Master Thesis Plan

Duration: October – March

Overview:

October : Determine the main direction/topic

November : Get familiar with the main paper and corresponding algorithm

December : Set up the environment for the whole research and collect date for further learning algorithm

January : Implement the main algorithm and test

February : Contribute to the main algorithm i.e. improve the NN or add some new approaches

March : Write the thesis

Detailed plan:

October :
10.19 - 10. 31 : Read papers and have online courses regarding to Deep learning and Reinforcement learning, Define the main topic and direction of the research.

November :
11.1 - 11.14 : Define main papers and think about the main simulator (Rlbench, Bullet simulator）
real robotic system.
11.15 - 11.30 : proceed the main paper and get familiar with the main algorithm

December :
12.1 - 12.14 : set up the environment including the virtual environment and the preparation of the robotic system.
12.15 - 12.31 : Collect the data (from real robot or directly from the data set online or from the simulator) and data pre – processing for further learning algorithm

January :
1.1 - 1.14 : implement the algorithm with the dataset
1.15 - 1.31 : Test the performance of the algorithm and compare with other algorithm

February :
2.1 - 2. 14 : Try to modify the NN and analyze the algorithm
2.15 - 2.28 : Test the performance of modified NN or algorithm, Do the test on the real robotic system to see the performance and the generalization capability.

March :
Plot the figures and write the thesis.

Master thesis Topics

Ideas:

TASK : Grasping
Basic paper:
https://www.researchgate.net/profile/Dmitry_Kalashnikov2/publication/326029397_QT-Opt_Scalable_Deep_Reinforcement_Learning_for_Vision-Based_Robotic_Manipulation/links/5e9db1eda6fdcca78928bc6d/QT-Opt-Scalable-Deep-Reinforcement-Learning-for-Vision-Based-Robotic-Manipulation.pdf

Background:
Option1 : grasp matrix
Option2 : learning based method
    current approaches : predict “grasp poses” → choose best location → open loop planner to reach

Alternative : RL + Deep Neural networks, dynamic closed-loop control , policy performs pre-grasp manipulation enables dynamic disturbance.

Can be improved(maybe):

1. action space
former : 4D (dx,dy,dz,rz)
current: 6D pose action→ generalization

2. grippe → robot hand

https://journals.sagepub.com/doi/pdf/10.1177/0278364919887447

3. reward
Former : Grasp success detection depends on the image information
current : force sensor or haptic sensor

4. Input data
From simulator to real world data to enable generalization

https://openaccess.thecvf.com/content_CVPR_2019/papers/James_Sim-To-Real_via_Sim-To-Sim_Data-Efficient_Robotic_Grasping_via_Randomized-To-Canonical_Adaptation_Networks_CVPR_2019_paper.pdf

https://arxiv.org/pdf/1810.05687.pdf

Difficulties : Data collection, environment set up when implemented on the real robotic system

TASK : Peg in hole